## main
Release | Task/M | Date Reported | Date Started | Date Closed | Status | Tgt Close Date | Task | File/Line | Comment1 | Comment2 | Comment3 | Comment4
0.1 | 2 | 2020-11-27 | 2020-12-15 | 2020-12-20 | Closed |  | add other attributes, e.g. market variables, added one, to add more later | b
0.1 | 3 | 2020-11-27 | 2020-12-26 | 2020-12-26 | Closed |  | run on portfolio
0.1 | 10 | 2020-12-26 | 2020-12-31 | 2021-01-17 | Closed | 2021-01-07 | new data , e.g. aaii and category, % from highs
0.1 | 4 | 2020-11-28 | 2020-12-31 | 2021-01-02 | Closed | 2020-12-29 | mlflow / allegro.ai? | .
0.1 | 9 | 2020-12-26 | 2021-01-17 | 2021-01-17 | Closed | 2021-01-20 | hyper param , new models
0.1 | z |  | 2020-11-01 | 2021-01-17 | Closed | 2021-01-31 | Analysis release
0.2 | 14 | 2021-11-17 | 2021-01-23 | 2021-01-23 | Closed |  | finish model selection pipeline
0.2 | 5 | 2020-12-05 |  | 2021-01-23 | Closed |  | build app using Docker, Gunicorn | . | Running Docker Container With Gunicorn and Flask - DEV Community | C:\Stuff\Important\CareerNCollege\AdHoc\Git\learning-python\example-voting-app\vote\Dockerfile
0.2 | 15 | 2021-01-23 | 2021-02-06 |  | In Progress | 2021-01-31 | upgrade html to be json repeatable w react |  | Tutorial: Intro to React – React (reactjs.org) | https://www.fullstackpython.com/react.html | https://tiangolo.medium.com/react-in-docker-with-nginx-built-with-multi-stage-docker-builds-including-testing-8cc49d6ec305 | https://amlanscloud.com/reactappdeploy/ | https://react-jsonschema-form.readthedocs.io/en/latest/ | https://github.com/ahmedbesbes/React-App-Flask-SSL | https://medium.com/swlh/deploy-and-secure-a-react-flask-app-with-docker-and-nginx-768ca582863b | https://datagraphi.com/blog/post/2020/8/30/docker-guide-build-a-fully-production-ready-machine-learning-app-with-react-django-and-postgresql-on-docker
0.2 | 13 | 2021-01-11 |  |  |  |  | Use terraform to provision |  | https://deepu.tech/deploy-a-web-app-to-azure-app-service-using-terraform/ | https://docs.microsoft.com/en-us/azure/devops/pipelines/apps/cd/deploy-docker-webapp?view=azure-devops&tabs=java
0.2 | 8 | 2020-12-20 |  |  |  |  | more mkt variables
0.2 | 6 | 2020-12-05 |  |  |  |  | utilize Heroku | .
0.2 | 12 | 2020-12-27 |  |  |  |  | quantstats
0.2 | 11 | 2020-12-27 |  |  |  |  | ending portfolio as final trades
0.2 | 1 | 2020-11-27 |  |  |  |  | need to consider share splits and dividends | a 77
0.2 | z |  |  |  |  | 2021-03-31 | First app on Heroku or Azure Free (see 0.3)
0.3 | 7 | 2020-12-05 |  |  |  |  | / SQL postgres w JSON to store |  | https://stackabuse.com/adding-a-postgresql-database-to-a-node-js-app-on-heroku/ | https://towardsdatascience.com/airflow-how-to-refresh-stocks-data-while-you-sleep-part-1-a464514e45b7 | https://github.com/lsclovecode/Real-Time-Stock-Streaming-Pipeline
0.3 | z |  |  |  |  | 2021-06-30 | Azure free / Digital Ocean / Google Cloud Kubernetes |  | https://dev.to/kenessajr/deploy-a-react-app-to-digitalocean-using-github-actions-and-docker-4pln | https://cloud.google.com/sql | https://github.com/romanorac/pandas-analytics-server

## architecture
Backend (with analysis)
1 | read in portfolio from IB
2 | append own charactierstics
3 | append market data
4 | build models
5 | decide best model
6 | pickle file & show inputs via mlflow
7 | validation exhibits
Front end
1 | read in csv file w characteristics
2 | append market data
3 | run model
4 | force plot
5 | build model
6 | show inputs
7 | run shap summary
8 | return model to user?
9 | also allow someone to input model pickle + inputs